## Project Gantt Chart
Create a Gantt Chart in this worksheet. Enter title of this project in cell B1. Legend title is in cell I1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | PROJECT TITLE | [5 empty] | Legend:
Enter Company Name in cell B2. A legend is in cells I2 through AC2. | Company Name | [5 empty] | On Track |  |  |  |  | Low Risk |  |  |  |  | Med Risk |  |  |  |  | High Risk |  |  |  |  | Unassigned
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell F3 or allow the sample formula to find the smallest date value from the Gantt Data table. Project Start Date: label is in cell D3. | Project Lead |  | Project Start Date: |  | 2019-09-29
A Scrolling Increment is in cell F4. Months for the dates in row 5 are displayed starting in cells I4 through cell BL4. Do not modify these cells. They are auto updated based on the project start date in cell F3. |  |  | Scrolling Increment: |  | 0 |  | September | [6 empty] | October | [27 empty] | November
Cells I5 through BL5 contain the day number of the month for the Month represented in the cell block above each date cell and are auto calculated. Do not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | s | time axis 2019-09-29 to 2019-11-23
A scrollbar is in cells I6 through BL6. The increment for paging through the data is defined as 2 pages at a time and can be configured in the settings for the control bar. To jump forward or backward in the timeline, enter a value of 0 or higher in cell F4. A value of 0 takes you to the beginning of the chart.
This row contains headers for the project schedule that follows below them. Navigate from B7 through BL7 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I7 and continues through cell BL7. All project timeline charting is auto generated based on the category, start date and number of days entered in the Milestones table. | Milestone Description | Category | Must/ Should / Could | Progress | Start | No. Days | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Enter Project information starting in cell B9 through cell G9. Sample data is in cells B9 through G33. Enter Milestone Description, select a Category from the drop-down list, assign someone to the item, enter the progress, start date and number of days for the task to start charting. The next instruction is in cell A34. | Sprint 1: (general set up)
| 1. Home web page | Low Risk | Must | 100% | 2019-09-30 | 7
| 2. Nutrition web page | Low Risk | Must | 100% | 2019-09-30 | 7
| 3. Training web page | Low Risk | Must | 100% | 2019-09-30 | 7
| 4. Personal Trainer web page | Low Risk | Must | 100% | 2019-10-07 | 2
| 5. FAQ web page | Low Risk | Must | 100% | 2019-10-07 | 2
| 6. GDPR web page | Low Risk | Must | 100% | 2019-10-07 | 2
| 7. Header & footer on all pages. | Low Risk | Should | 100% | 2019-10-07 | 2
| 8. CSS | Milestone | Could | 100% | 2019-10-09 | 5 | bar: S to T
Sprint 2: (nutrition & training)
| 9. Nutrition document | Low Risk | Must | 100% | 2019-10-14 | 14
| 10. Bodybuilding document | Low Risk | Must | 100% | 2019-10-14 | 14
| 11. Nutrition web page | Med Risk | Should | 100% | 2019-10-28 | 5
| 12. Bodybuilding training web page | Med Risk | Should | 100% | 2019-10-28 | 5
| 13. Hybrid training web page | Milestone | Could | 100% | 2019-10-28 | 5
Sprint 3: (log in & sign up)
| 14. Sign up (database) | High Risk | Must | 100% | 2019-11-04 | 14
| 15. Sign up client page (html / css) | Med Risk | Must | 100% | 2019-11-13 | 5
| 16. Sign up personal trainer page (html / css) | Low Risk | Must | 100% | 2019-11-18 | 5
| 17. Log in client page (html / css / php) | Low Risk | Must | 100% | 2019-11-18 | 5
| 18. Log in personal trainer page (html / css / php) | Med Risk | Should | 100% | 2019-11-23 | 5
| 19. Log out | Med Risk | Should | 100% | 2019-11-23 | 5
| 20. Log in CSS | Med Risk | Could | 100% | 2019-11-28 | 5
| 21. Sign up CSS | Milestone | Could | 100% | 2019-11-28 | 5
Sprint 4: (nutrition)
| 22. Disclaimer; GP, legal & ethical. | High Risk | Must | 100% | 2019-12-03 | 1
| 23. Intro to nutrition, calories. | Med Risk | Must | 100% | 2019-12-03 | 7
| 24. Intro to nutrition, macros. | Med Risk | Must | 100% | 2019-12-10 | 7
| 25. Weight loss section. | Low Risk | Should | 100% | 2019-12-03 | 5
| 26. Weight gain section. | Low Risk | Should | 100% | 2019-12-10 | 5
| 27. Weight maintenance section. | Low Risk | Should | 100% | 2019-12-15 | 5
| 28. Supplements section | Milestone | Could | 100% | 2019-12-20 | 5
Sprint 5: (training)
| 29. Bodybuilding training program. | Low Risk | Must | 100% | 2020-01-03 | 21
| 31. Hybrid training program. | Low Risk | Must | 100% | 2020-01-03 | 21
| 32. Can download training programs. | Low Risk | Should | 100% | 2020-01-13 | 1
| 33. 1 rep max calc (more than 1 rep function). | Low Risk | Should | 0% | 2020-01-24 | 1
| 34. Abbreviation dictionary. | Low Risk | Should | 0% | 2020-01-24 | 1
| 35. Explanation of training block. | Low Risk | Should | 50% | 2020-01-03 | 7
| 36. Create own training program. | Med Risk | Could | 0% | 2020-01-24 | 7
| 37. Reminder when training blocks start & end. | Med Risk | Could | 0% | 2020-01-24 | 7
Sprint 6: (GDPR & Index Page)
| 39. GDPR relevant article | Med Risk | Must | 100% | 2020-02-03 | 2
| 40. GDPR laws compliant | High Risk | Must | 100% | 2020-02-03 | 7
| 41. Links & contact info for laws | Low Risk | Should | 100% | 2020-02-10 | 1
| 42. Links & short write up | Low Risk | Could | 100% | 2020-02-10 | 1
Sprint 7: (Responsiveness)
| 43. Top navigation menu | High Risk | Must | 100% | 2020-02-11 | 21
| 44. Log In system menu integrated | High Risk | Must | 100% | 2020-02-25 | 14
| 45. Table | Low Risk | Should | 100% | 2020-02-11 | 2
| 46. Images | Low Risk | Should | 100% | 2020-02-11 | 1
| 47. Side navigation menu | Low Risk | Could | 0% | 2020-02-25 | 14
| 48. Forms | Low Risk | Could | 100% | 2020-03-09 | 1
Sprint 8: (Client page)
| 49. Upload data; e.g. weight, height, etc… | High Risk | Must | 100% | 2020-03-09 | 14
| 50. Visual representation of data; e.g. graph. | Med Risk | Should | 0% | 2020-03-23 | 7
| 51. Access to training programs. | High Risk | Should | 0% | 2020-03-23 | 7
| 52. Access to diet programs. | High Risk | Should | 0% | 2020-03-30 | 7
| 53. Book training session. | High Risk | Should | 0% | 2020-03-30 | 7
| 54. Access to PT information. | High Risk | Could | 0% | 2020-04-06 | 7
Sprint 9: (PT page)
| 1. Upload personal info | High Risk | Must | 100% | 2020-04-13 | 7
| 2. Check for valid degrees. | High Risk | Must | 100% | 2020-04-13 | 7
| 3. Upload diet programs. | Med Risk | Should | 0% | 2020-04-20 | 7
| 4. Upload training programs. | Med Risk | Should | 0% | 2020-04-20 | 7
| 5. Book training sessions. | Med Risk | Should | 0% | 2020-04-27 | 7
| 6. Upload contact info. | Low Risk | Could | 0% | 2020-04-27 | 7
Sprint 10: (Pushed back)
| 61. Weight maintenance section. | Low Risk | Should | 100% | 2020-05-04 | 7
| 62. Supplements section | Low Risk | Could | 100% | 2020-05-04 | 7
| 63. MyFitnessPal | Low Risk | Could | 100% | 2020-05-11 | 7
| 64. Can download training programs. | Low Risk | Should | 100% | 2020-05-11 | 1
| 65. 1 rep max calc (more than 1 rep function). | Low Risk | Should | 0% | 2020-05-04 | 2
| 66. Abbreviation dictionary. | Low Risk | Should | 0% | 2020-05-06 | 7
| 67. Explanation of training block. | Low Risk | Should | 100% | 2020-05-03 | 7
| 68. Create own training program. | Med Risk | Could | 0% | 2020-05-18 | 14
| 69. Reminder when training blocks start & end. | Med Risk | Could | 0% | 2020-05-18 | 7
| SUBMITTION DATE |  | Must |  | 2020-05-25 | 1
Must
Should
Could